## Open
capa_id | title | site | area | owner | status | created_date | due_date | closed_date | root_cause_complete | actions_complete | verification_complete | effectiveness_complete | is_closed | age_days | days_to_due | is_overdue | is_due_soon | missing_root_cause | missing_actions | missing_verification | missing_effectiveness | missing_info_count | blockers | triage_bucket | triage_score | ready_to_close | age_bucket
CAPA-0025 | Data backup gaps | Site A | Operations | Owner D | VE | 2026-07-03 | 2026-08-08 |  | Y | Y | N | Y | FALSE | 90 | -54 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 60+
CAPA-0041 | Hold/release timing | Site A | QA | Owner D | CP | 2026-07-03 | 2026-07-23 |  | Y | N | N | N | FALSE | 90 | -70 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0033 | Temperature log gaps | Site B | Sanitation | Owner B | RC | 2026-07-10 | 2026-08-30 |  | Y | N | N | N | FALSE | 83 | -32 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0059 | Calibration tracking gaps | Site A | Warehouse | Owner C | PD | 2026-07-11 | 2026-08-09 |  | N | N | N | N | FALSE | 82 | -53 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0031 | Sampling SOP update | Site B | QA | Owner B | VE | 2026-07-15 | 2026-08-11 |  | Y | Y | Y | N | FALSE | 78 | -51 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0005 | Temperature log gaps | Site A | Warehouse | Owner B | PD | 2026-07-16 | 2026-08-22 |  | N | N | N | N | FALSE | 77 | -40 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0026 | Label traceability | Site B | QA | Owner A | PD | 2026-07-16 | 2026-08-12 |  | N | N | N | N | FALSE | 77 | -50 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0029 | Training record gaps | Site C | Sanitation | Owner E | PD | 2026-07-19 | 2026-08-15 |  | N | N | N | N | FALSE | 74 | -47 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0015 | Temperature log gaps | Site A | Operations | Owner E | CP | 2026-07-21 | 2026-09-18 |  | Y | Y | N | N | FALSE | 72 | -13 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0040 | Deviation documentation | Site C | Micro Lab | Owner D | VE | 2026-07-22 | 2026-09-16 |  | Y | Y | Y | N | FALSE | 71 | -15 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0053 | Data backup gaps | Site A | Operations | Owner D | VE | 2026-07-23 | 2026-08-07 |  | Y | Y | N | Y | FALSE | 70 | -55 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 60+
CAPA-0054 | Label traceability | Site B | Warehouse | Owner D | VE | 2026-07-27 | 2026-09-14 |  | Y | Y | Y | N | FALSE | 66 | -17 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0057 | Temperature log gaps | Site C | IT/QA | Owner A | CP | 2026-07-28 | 2026-09-11 |  | Y | Y | N | N | FALSE | 65 | -20 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0002 | Training record gaps | Site B | Operations | Owner A | CP | 2026-08-01 | 2026-08-23 |  | Y | Y | N | N | FALSE | 61 | -39 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0036 | Label traceability | Site A | Micro Lab | Owner D | PD | 2026-08-02 | 2026-08-29 |  | N | N | N | N | FALSE | 60 | -33 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0042 | Equipment list mismatch | Site C | QA | Owner A | VE | 2026-08-02 | 2026-09-06 |  | Y | Y | Y | N | FALSE | 60 | -25 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0010 | Training record gaps | Site C | IT/QA | Owner C | CP | 2026-08-04 | 2026-09-01 |  | Y | Y | N | N | FALSE | 58 | -30 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0017 | Sampling SOP update | Site C | Warehouse | Owner E | CP | 2026-08-07 | 2026-09-06 |  | Y | N | N | N | FALSE | 55 | -25 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0009 | Deviation documentation | Site C | Operations | Owner E | PD | 2026-08-10 | 2026-09-04 |  | N | N | N | N | FALSE | 52 | -27 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0011 | Chemical identification gaps | Site B | IT/QA | Owner B | RC | 2026-08-11 | 2026-09-26 |  | Y | N | N | N | FALSE | 51 | -5 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0014 | Environmental monitoring gaps | Site B | Micro Lab | Owner B | VE | 2026-08-11 | 2026-09-11 |  | Y | Y | N | Y | FALSE | 51 | -20 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 31–60
CAPA-0038 | Equipment list mismatch | Site A | Micro Lab | Owner D | CP | 2026-08-11 | 2026-08-30 |  | Y | Y | N | N | FALSE | 51 | -32 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0039 | Calibration tracking gaps | Site A | Sanitation | Owner D | RC | 2026-08-16 | 2026-09-20 |  | Y | N | N | N | FALSE | 46 | -11 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0060 | Sampling SOP update | Site B | Micro Lab | Owner C | PD | 2026-08-16 | 2026-09-28 |  | N | N | N | N | FALSE | 46 | -3 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0044 | Training record gaps | Site A | Micro Lab | Owner C | RC | 2026-08-25 | 2026-09-18 |  | Y | N | N | N | FALSE | 37 | -13 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0056 | Calibration tracking gaps | Site B | Operations | Owner B | VE | 2026-08-20 | 2026-10-07 |  | Y | Y | Y | N | FALSE | 42 | 6 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0035 | Calibration tracking gaps | Site C | Warehouse | Owner C | CP | 2026-08-22 | 2026-10-09 |  | Y | Y | N | N | FALSE | 40 | 8 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0045 | Environmental monitoring gaps | Site B | Warehouse | Owner B | VE | 2026-08-24 | 2026-10-11 |  | Y | Y | N | Y | FALSE | 38 | 10 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | DUE_SOON | 5 | FALSE | 31–60
CAPA-0049 | Label traceability | Site C | IT/QA | Owner E | VE | 2026-08-31 | 2026-10-10 |  | Y | Y | Y | N | FALSE | 31 | 9 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0016 | Training record gaps | Site B | Micro Lab | Owner C | RC | 2026-09-03 | 2026-09-22 |  | Y | N | N | N | FALSE | 28 | -9 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 5 | FALSE | 15–30
CAPA-0021 | Sampling SOP update | Site C | QA | Owner A | VE | 2026-07-04 | 2026-08-04 |  | Y | Y | Y | Y | FALSE | 89 | -58 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0046 | Hold/release timing | Site B | Sanitation | Owner C | VE | 2026-07-19 | 2026-08-17 |  | Y | Y | Y | Y | FALSE | 74 | -45 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0008 | Label traceability | Site A | QA | Owner C | VE | 2026-07-24 | 2026-08-25 |  | Y | Y | Y | Y | FALSE | 69 | -37 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0055 | Equipment list mismatch | Site A | IT/QA | Owner B | VE | 2026-07-30 | 2026-09-05 |  | Y | Y | Y | Y | FALSE | 63 | -26 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0019 | Calibration tracking gaps | Site C | Packaging | Owner A | VE | 2026-08-30 | 2026-09-29 |  | Y | Y | Y | Y | FALSE | 32 | -2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 31–60
CAPA-0034 | Deviation documentation | Site C | QA | Owner E | RC | 2026-09-04 | 2026-10-09 |  | N | N | N | N | FALSE | 27 | 8 | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | DUE_SOON | 4 | FALSE | 15–30
CAPA-0037 | Sampling SOP update | Site B | Warehouse | Owner D | PD | 2026-09-19 | 2026-10-07 |  | N | N | N | N | FALSE | 12 | 6 | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | DUE_SOON | 4 | FALSE | 0–14
CAPA-0007 | Environmental monitoring gaps | Site B | QA | Owner D | VE | 2026-09-23 | 2026-10-15 |  | Y | Y | Y | N | FALSE | 8 | 14 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 4 | FALSE | 0–14
CAPA-0004 | Label traceability | Site B | Warehouse | Owner B | VE | 2026-08-19 | 2026-10-05 |  | Y | Y | Y | Y | FALSE | 43 | 4 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 0 | None | DUE_SOON | 3 | TRUE | 31–60
CAPA-0020 | Hold/release timing | Site A | QA | Owner E | CP | 2026-08-22 | 2026-10-20 |  | Y | Y | N | N | FALSE | 40 | 19 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | MISSING_INFO | 3 | FALSE | 31–60
CAPA-0043 | Data backup gaps | Site B | IT/QA | Owner E | VE | 2026-08-25 | 2026-10-11 |  | Y | Y | Y | Y | FALSE | 37 | 10 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 0 | None | DUE_SOON | 3 | TRUE | 31–60
CAPA-0047 | Temperature log gaps | Site C | Warehouse | Owner E | RC | 2026-09-02 | 2026-10-24 |  | N | N | N | N | FALSE | 29 | 23 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0028 | Temperature log gaps | Site C | Operations | Owner E | PD | 2026-09-09 | 2026-11-07 |  | N | N | N | N | FALSE | 22 | 37 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0022 | Calibration tracking gaps | Site B | IT/QA | Owner A | RC | 2026-09-11 | 2026-11-06 |  | Y | N | N | N | FALSE | 20 | 36 | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0048 | Deviation documentation | Site B | Sanitation | Owner E | RC | 2026-09-15 | 2026-10-26 |  | N | N | N | N | FALSE | 16 | 25 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0058 | Chemical identification gaps | Site B | IT/QA | Owner A | CP | 2026-09-16 | 2026-10-20 |  | Y | N | N | N | FALSE | 15 | 19 | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0051 | Hold/release timing | Site C | IT/QA | Owner D | PD | 2026-09-21 | 2026-10-27 |  | N | N | N | N | FALSE | 10 | 26 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0013 | Deviation documentation | Site B | Operations | Owner A | VE | 2026-09-22 | 2026-11-03 |  | Y | Y | N | Y | FALSE | 9 | 33 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0052 | Label traceability | Site B | Packaging | Owner B | PD | 2026-09-22 | 2026-11-15 |  | N | N | N | N | FALSE | 9 | 45 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0030 | Training record gaps | Site C | QA | Owner E | VE | 2026-09-25 | 2026-11-14 |  | Y | Y | Y | N | FALSE | 6 | 44 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0027 | Calibration tracking gaps | Site A | Operations | Owner E | CP | 2026-09-27 | 2026-11-16 |  | Y | Y | N | N | FALSE | 4 | 46 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0018 | Sampling SOP update | Site A | Sanitation | Owner A | PD | 2026-09-28 | 2026-10-18 |  | N | N | N | N | FALSE | 3 | 17 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0050 | Deviation documentation | Site C | Packaging | Owner C | PD | 2026-09-28 | 2026-10-21 |  | N | N | N | N | FALSE | 3 | 20 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0001 | Calibration tracking gaps | Site A | Operations | Owner C | VE | 2026-08-22 | 2026-10-19 |  | Y | Y | Y | Y | FALSE | 40 | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OK | 1 | TRUE | 31–60

## Overdue
capa_id | title | site | area | owner | status | created_date | due_date | closed_date | root_cause_complete | actions_complete | verification_complete | effectiveness_complete | is_closed | age_days | days_to_due | is_overdue | is_due_soon | missing_root_cause | missing_actions | missing_verification | missing_effectiveness | missing_info_count | blockers | triage_bucket | triage_score | ready_to_close | age_bucket
CAPA-0025 | Data backup gaps | Site A | Operations | Owner D | VE | 2026-07-03 | 2026-08-08 |  | Y | Y | N | Y | FALSE | 90 | -54 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 60+
CAPA-0041 | Hold/release timing | Site A | QA | Owner D | CP | 2026-07-03 | 2026-07-23 |  | Y | N | N | N | FALSE | 90 | -70 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0033 | Temperature log gaps | Site B | Sanitation | Owner B | RC | 2026-07-10 | 2026-08-30 |  | Y | N | N | N | FALSE | 83 | -32 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0059 | Calibration tracking gaps | Site A | Warehouse | Owner C | PD | 2026-07-11 | 2026-08-09 |  | N | N | N | N | FALSE | 82 | -53 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0031 | Sampling SOP update | Site B | QA | Owner B | VE | 2026-07-15 | 2026-08-11 |  | Y | Y | Y | N | FALSE | 78 | -51 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0005 | Temperature log gaps | Site A | Warehouse | Owner B | PD | 2026-07-16 | 2026-08-22 |  | N | N | N | N | FALSE | 77 | -40 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0026 | Label traceability | Site B | QA | Owner A | PD | 2026-07-16 | 2026-08-12 |  | N | N | N | N | FALSE | 77 | -50 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0029 | Training record gaps | Site C | Sanitation | Owner E | PD | 2026-07-19 | 2026-08-15 |  | N | N | N | N | FALSE | 74 | -47 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0015 | Temperature log gaps | Site A | Operations | Owner E | CP | 2026-07-21 | 2026-09-18 |  | Y | Y | N | N | FALSE | 72 | -13 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0040 | Deviation documentation | Site C | Micro Lab | Owner D | VE | 2026-07-22 | 2026-09-16 |  | Y | Y | Y | N | FALSE | 71 | -15 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0053 | Data backup gaps | Site A | Operations | Owner D | VE | 2026-07-23 | 2026-08-07 |  | Y | Y | N | Y | FALSE | 70 | -55 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 60+
CAPA-0054 | Label traceability | Site B | Warehouse | Owner D | VE | 2026-07-27 | 2026-09-14 |  | Y | Y | Y | N | FALSE | 66 | -17 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0057 | Temperature log gaps | Site C | IT/QA | Owner A | CP | 2026-07-28 | 2026-09-11 |  | Y | Y | N | N | FALSE | 65 | -20 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0002 | Training record gaps | Site B | Operations | Owner A | CP | 2026-08-01 | 2026-08-23 |  | Y | Y | N | N | FALSE | 61 | -39 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0036 | Label traceability | Site A | Micro Lab | Owner D | PD | 2026-08-02 | 2026-08-29 |  | N | N | N | N | FALSE | 60 | -33 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0042 | Equipment list mismatch | Site C | QA | Owner A | VE | 2026-08-02 | 2026-09-06 |  | Y | Y | Y | N | FALSE | 60 | -25 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0010 | Training record gaps | Site C | IT/QA | Owner C | CP | 2026-08-04 | 2026-09-01 |  | Y | Y | N | N | FALSE | 58 | -30 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0017 | Sampling SOP update | Site C | Warehouse | Owner E | CP | 2026-08-07 | 2026-09-06 |  | Y | N | N | N | FALSE | 55 | -25 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0009 | Deviation documentation | Site C | Operations | Owner E | PD | 2026-08-10 | 2026-09-04 |  | N | N | N | N | FALSE | 52 | -27 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0011 | Chemical identification gaps | Site B | IT/QA | Owner B | RC | 2026-08-11 | 2026-09-26 |  | Y | N | N | N | FALSE | 51 | -5 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0014 | Environmental monitoring gaps | Site B | Micro Lab | Owner B | VE | 2026-08-11 | 2026-09-11 |  | Y | Y | N | Y | FALSE | 51 | -20 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 31–60
CAPA-0038 | Equipment list mismatch | Site A | Micro Lab | Owner D | CP | 2026-08-11 | 2026-08-30 |  | Y | Y | N | N | FALSE | 51 | -32 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0039 | Calibration tracking gaps | Site A | Sanitation | Owner D | RC | 2026-08-16 | 2026-09-20 |  | Y | N | N | N | FALSE | 46 | -11 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0060 | Sampling SOP update | Site B | Micro Lab | Owner C | PD | 2026-08-16 | 2026-09-28 |  | N | N | N | N | FALSE | 46 | -3 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0044 | Training record gaps | Site A | Micro Lab | Owner C | RC | 2026-08-25 | 2026-09-18 |  | Y | N | N | N | FALSE | 37 | -13 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0016 | Training record gaps | Site B | Micro Lab | Owner C | RC | 2026-09-03 | 2026-09-22 |  | Y | N | N | N | FALSE | 28 | -9 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 5 | FALSE | 15–30
CAPA-0021 | Sampling SOP update | Site C | QA | Owner A | VE | 2026-07-04 | 2026-08-04 |  | Y | Y | Y | Y | FALSE | 89 | -58 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0046 | Hold/release timing | Site B | Sanitation | Owner C | VE | 2026-07-19 | 2026-08-17 |  | Y | Y | Y | Y | FALSE | 74 | -45 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0008 | Label traceability | Site A | QA | Owner C | VE | 2026-07-24 | 2026-08-25 |  | Y | Y | Y | Y | FALSE | 69 | -37 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0055 | Equipment list mismatch | Site A | IT/QA | Owner B | VE | 2026-07-30 | 2026-09-05 |  | Y | Y | Y | Y | FALSE | 63 | -26 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0019 | Calibration tracking gaps | Site C | Packaging | Owner A | VE | 2026-08-30 | 2026-09-29 |  | Y | Y | Y | Y | FALSE | 32 | -2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 31–60

## DueSoon
capa_id | title | site | area | owner | status | created_date | due_date | closed_date | root_cause_complete | actions_complete | verification_complete | effectiveness_complete | is_closed | age_days | days_to_due | is_overdue | is_due_soon | missing_root_cause | missing_actions | missing_verification | missing_effectiveness | missing_info_count | blockers | triage_bucket | triage_score | ready_to_close | age_bucket
CAPA-0056 | Calibration tracking gaps | Site B | Operations | Owner B | VE | 2026-08-20 | 2026-10-07 |  | Y | Y | Y | N | FALSE | 42 | 6 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0035 | Calibration tracking gaps | Site C | Warehouse | Owner C | CP | 2026-08-22 | 2026-10-09 |  | Y | Y | N | N | FALSE | 40 | 8 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0045 | Environmental monitoring gaps | Site B | Warehouse | Owner B | VE | 2026-08-24 | 2026-10-11 |  | Y | Y | N | Y | FALSE | 38 | 10 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | DUE_SOON | 5 | FALSE | 31–60
CAPA-0049 | Label traceability | Site C | IT/QA | Owner E | VE | 2026-08-31 | 2026-10-10 |  | Y | Y | Y | N | FALSE | 31 | 9 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0034 | Deviation documentation | Site C | QA | Owner E | RC | 2026-09-04 | 2026-10-09 |  | N | N | N | N | FALSE | 27 | 8 | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | DUE_SOON | 4 | FALSE | 15–30
CAPA-0037 | Sampling SOP update | Site B | Warehouse | Owner D | PD | 2026-09-19 | 2026-10-07 |  | N | N | N | N | FALSE | 12 | 6 | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | DUE_SOON | 4 | FALSE | 0–14
CAPA-0007 | Environmental monitoring gaps | Site B | QA | Owner D | VE | 2026-09-23 | 2026-10-15 |  | Y | Y | Y | N | FALSE | 8 | 14 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 4 | FALSE | 0–14
CAPA-0004 | Label traceability | Site B | Warehouse | Owner B | VE | 2026-08-19 | 2026-10-05 |  | Y | Y | Y | Y | FALSE | 43 | 4 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 0 | None | DUE_SOON | 3 | TRUE | 31–60
CAPA-0043 | Data backup gaps | Site B | IT/QA | Owner E | VE | 2026-08-25 | 2026-10-11 |  | Y | Y | Y | Y | FALSE | 37 | 10 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 0 | None | DUE_SOON | 3 | TRUE | 31–60

## MissingInfo
capa_id | title | site | area | owner | status | created_date | due_date | closed_date | root_cause_complete | actions_complete | verification_complete | effectiveness_complete | is_closed | age_days | days_to_due | is_overdue | is_due_soon | missing_root_cause | missing_actions | missing_verification | missing_effectiveness | missing_info_count | blockers | triage_bucket | triage_score | ready_to_close | age_bucket
CAPA-0025 | Data backup gaps | Site A | Operations | Owner D | VE | 2026-07-03 | 2026-08-08 |  | Y | Y | N | Y | FALSE | 90 | -54 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 60+
CAPA-0041 | Hold/release timing | Site A | QA | Owner D | CP | 2026-07-03 | 2026-07-23 |  | Y | N | N | N | FALSE | 90 | -70 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0033 | Temperature log gaps | Site B | Sanitation | Owner B | RC | 2026-07-10 | 2026-08-30 |  | Y | N | N | N | FALSE | 83 | -32 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0059 | Calibration tracking gaps | Site A | Warehouse | Owner C | PD | 2026-07-11 | 2026-08-09 |  | N | N | N | N | FALSE | 82 | -53 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0031 | Sampling SOP update | Site B | QA | Owner B | VE | 2026-07-15 | 2026-08-11 |  | Y | Y | Y | N | FALSE | 78 | -51 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0005 | Temperature log gaps | Site A | Warehouse | Owner B | PD | 2026-07-16 | 2026-08-22 |  | N | N | N | N | FALSE | 77 | -40 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0026 | Label traceability | Site B | QA | Owner A | PD | 2026-07-16 | 2026-08-12 |  | N | N | N | N | FALSE | 77 | -50 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0029 | Training record gaps | Site C | Sanitation | Owner E | PD | 2026-07-19 | 2026-08-15 |  | N | N | N | N | FALSE | 74 | -47 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0015 | Temperature log gaps | Site A | Operations | Owner E | CP | 2026-07-21 | 2026-09-18 |  | Y | Y | N | N | FALSE | 72 | -13 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0040 | Deviation documentation | Site C | Micro Lab | Owner D | VE | 2026-07-22 | 2026-09-16 |  | Y | Y | Y | N | FALSE | 71 | -15 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0053 | Data backup gaps | Site A | Operations | Owner D | VE | 2026-07-23 | 2026-08-07 |  | Y | Y | N | Y | FALSE | 70 | -55 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 60+
CAPA-0054 | Label traceability | Site B | Warehouse | Owner D | VE | 2026-07-27 | 2026-09-14 |  | Y | Y | Y | N | FALSE | 66 | -17 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0057 | Temperature log gaps | Site C | IT/QA | Owner A | CP | 2026-07-28 | 2026-09-11 |  | Y | Y | N | N | FALSE | 65 | -20 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0002 | Training record gaps | Site B | Operations | Owner A | CP | 2026-08-01 | 2026-08-23 |  | Y | Y | N | N | FALSE | 61 | -39 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 60+
CAPA-0036 | Label traceability | Site A | Micro Lab | Owner D | PD | 2026-08-02 | 2026-08-29 |  | N | N | N | N | FALSE | 60 | -33 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0042 | Equipment list mismatch | Site C | QA | Owner A | VE | 2026-08-02 | 2026-09-06 |  | Y | Y | Y | N | FALSE | 60 | -25 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0010 | Training record gaps | Site C | IT/QA | Owner C | CP | 2026-08-04 | 2026-09-01 |  | Y | Y | N | N | FALSE | 58 | -30 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0017 | Sampling SOP update | Site C | Warehouse | Owner E | CP | 2026-08-07 | 2026-09-06 |  | Y | N | N | N | FALSE | 55 | -25 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0009 | Deviation documentation | Site C | Operations | Owner E | PD | 2026-08-10 | 2026-09-04 |  | N | N | N | N | FALSE | 52 | -27 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0011 | Chemical identification gaps | Site B | IT/QA | Owner B | RC | 2026-08-11 | 2026-09-26 |  | Y | N | N | N | FALSE | 51 | -5 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0014 | Environmental monitoring gaps | Site B | Micro Lab | Owner B | VE | 2026-08-11 | 2026-09-11 |  | Y | Y | N | Y | FALSE | 51 | -20 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | OVERDUE | 6 | FALSE | 31–60
CAPA-0038 | Equipment list mismatch | Site A | Micro Lab | Owner D | CP | 2026-08-11 | 2026-08-30 |  | Y | Y | N | N | FALSE | 51 | -32 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0039 | Calibration tracking gaps | Site A | Sanitation | Owner D | RC | 2026-08-16 | 2026-09-20 |  | Y | N | N | N | FALSE | 46 | -11 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0060 | Sampling SOP update | Site B | Micro Lab | Owner C | PD | 2026-08-16 | 2026-09-28 |  | N | N | N | N | FALSE | 46 | -3 | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0044 | Training record gaps | Site A | Micro Lab | Owner C | RC | 2026-08-25 | 2026-09-18 |  | Y | N | N | N | FALSE | 37 | -13 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 6 | FALSE | 31–60
CAPA-0056 | Calibration tracking gaps | Site B | Operations | Owner B | VE | 2026-08-20 | 2026-10-07 |  | Y | Y | Y | N | FALSE | 42 | 6 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0035 | Calibration tracking gaps | Site C | Warehouse | Owner C | CP | 2026-08-22 | 2026-10-09 |  | Y | Y | N | N | FALSE | 40 | 8 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0045 | Environmental monitoring gaps | Site B | Warehouse | Owner B | VE | 2026-08-24 | 2026-10-11 |  | Y | Y | N | Y | FALSE | 38 | 10 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | DUE_SOON | 5 | FALSE | 31–60
CAPA-0049 | Label traceability | Site C | IT/QA | Owner E | VE | 2026-08-31 | 2026-10-10 |  | Y | Y | Y | N | FALSE | 31 | 9 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 5 | FALSE | 31–60
CAPA-0016 | Training record gaps | Site B | Micro Lab | Owner C | RC | 2026-09-03 | 2026-09-22 |  | Y | N | N | N | FALSE | 28 | -9 | TRUE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | OVERDUE | 5 | FALSE | 15–30
CAPA-0034 | Deviation documentation | Site C | QA | Owner E | RC | 2026-09-04 | 2026-10-09 |  | N | N | N | N | FALSE | 27 | 8 | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | DUE_SOON | 4 | FALSE | 15–30
CAPA-0037 | Sampling SOP update | Site B | Warehouse | Owner D | PD | 2026-09-19 | 2026-10-07 |  | N | N | N | N | FALSE | 12 | 6 | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | DUE_SOON | 4 | FALSE | 0–14
CAPA-0007 | Environmental monitoring gaps | Site B | QA | Owner D | VE | 2026-09-23 | 2026-10-15 |  | Y | Y | Y | N | FALSE | 8 | 14 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | DUE_SOON | 4 | FALSE | 0–14
CAPA-0020 | Hold/release timing | Site A | QA | Owner E | CP | 2026-08-22 | 2026-10-20 |  | Y | Y | N | N | FALSE | 40 | 19 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | MISSING_INFO | 3 | FALSE | 31–60
CAPA-0047 | Temperature log gaps | Site C | Warehouse | Owner E | RC | 2026-09-02 | 2026-10-24 |  | N | N | N | N | FALSE | 29 | 23 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0028 | Temperature log gaps | Site C | Operations | Owner E | PD | 2026-09-09 | 2026-11-07 |  | N | N | N | N | FALSE | 22 | 37 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0022 | Calibration tracking gaps | Site B | IT/QA | Owner A | RC | 2026-09-11 | 2026-11-06 |  | Y | N | N | N | FALSE | 20 | 36 | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0048 | Deviation documentation | Site B | Sanitation | Owner E | RC | 2026-09-15 | 2026-10-26 |  | N | N | N | N | FALSE | 16 | 25 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0058 | Chemical identification gaps | Site B | IT/QA | Owner A | CP | 2026-09-16 | 2026-10-20 |  | Y | N | N | N | FALSE | 15 | 19 | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | 3 | Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 15–30
CAPA-0051 | Hold/release timing | Site C | IT/QA | Owner D | PD | 2026-09-21 | 2026-10-27 |  | N | N | N | N | FALSE | 10 | 26 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0013 | Deviation documentation | Site B | Operations | Owner A | VE | 2026-09-22 | 2026-11-03 |  | Y | Y | N | Y | FALSE | 9 | 33 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 1 | Verification | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0052 | Label traceability | Site B | Packaging | Owner B | PD | 2026-09-22 | 2026-11-15 |  | N | N | N | N | FALSE | 9 | 45 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0030 | Training record gaps | Site C | QA | Owner E | VE | 2026-09-25 | 2026-11-14 |  | Y | Y | Y | N | FALSE | 6 | 44 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 1 | Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0027 | Calibration tracking gaps | Site A | Operations | Owner E | CP | 2026-09-27 | 2026-11-16 |  | Y | Y | N | N | FALSE | 4 | 46 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2 | Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0018 | Sampling SOP update | Site A | Sanitation | Owner A | PD | 2026-09-28 | 2026-10-18 |  | N | N | N | N | FALSE | 3 | 17 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14
CAPA-0050 | Deviation documentation | Site C | Packaging | Owner C | PD | 2026-09-28 | 2026-10-21 |  | N | N | N | N | FALSE | 3 | 20 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 4 | Root Cause, Actions, Verification, Effectiveness | MISSING_INFO | 2 | FALSE | 0–14

## ClosureReady
capa_id | title | site | area | owner | status | created_date | due_date | closed_date | root_cause_complete | actions_complete | verification_complete | effectiveness_complete | is_closed | age_days | days_to_due | is_overdue | is_due_soon | missing_root_cause | missing_actions | missing_verification | missing_effectiveness | missing_info_count | blockers | triage_bucket | triage_score | ready_to_close | age_bucket
CAPA-0021 | Sampling SOP update | Site C | QA | Owner A | VE | 2026-07-04 | 2026-08-04 |  | Y | Y | Y | Y | FALSE | 89 | -58 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0046 | Hold/release timing | Site B | Sanitation | Owner C | VE | 2026-07-19 | 2026-08-17 |  | Y | Y | Y | Y | FALSE | 74 | -45 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0008 | Label traceability | Site A | QA | Owner C | VE | 2026-07-24 | 2026-08-25 |  | Y | Y | Y | Y | FALSE | 69 | -37 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0055 | Equipment list mismatch | Site A | IT/QA | Owner B | VE | 2026-07-30 | 2026-09-05 |  | Y | Y | Y | Y | FALSE | 63 | -26 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 60+
CAPA-0019 | Calibration tracking gaps | Site C | Packaging | Owner A | VE | 2026-08-30 | 2026-09-29 |  | Y | Y | Y | Y | FALSE | 32 | -2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OVERDUE | 4 | TRUE | 31–60
CAPA-0004 | Label traceability | Site B | Warehouse | Owner B | VE | 2026-08-19 | 2026-10-05 |  | Y | Y | Y | Y | FALSE | 43 | 4 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 0 | None | DUE_SOON | 3 | TRUE | 31–60
CAPA-0043 | Data backup gaps | Site B | IT/QA | Owner E | VE | 2026-08-25 | 2026-10-11 |  | Y | Y | Y | Y | FALSE | 37 | 10 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | 0 | None | DUE_SOON | 3 | TRUE | 31–60
CAPA-0001 | Calibration tracking gaps | Site A | Operations | Owner C | VE | 2026-08-22 | 2026-10-19 |  | Y | Y | Y | Y | FALSE | 40 | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | None | OK | 1 | TRUE | 31–60

## Summary
metric | count
Open CAPAs | 54
Overdue | 31
Due Soon | 9
Missing Closure Info | 46
Closure Ready | 8